## Sheet1
Date | Task
2026-04-08 | Completed Ethics form and sent to supervisor for approval.
2026-04-09 | Gather data sources and shortlisted potential study areas, ethics form approved by supervisor and submitted.
2026-04-09 | Setup a GitHub repository for data preparation and pre-validation purpose.
2026-04-15 | Data pre-validation for satellite imagery for shortlisted study areas via Google Earth Engine completed, confirmed study area, downloaded r5r required data files and converted data into GTFS format.
2026-05-13 | Data pre-validation resumed, noticed missing data problems with the converted GTFS data, found an alternative dataset (as supported by literature).
2026-05-19 | Finalised research questions and objectives and started drafting introduction.
2026-05-23 | Finished first draft introduction, start literature review.
2026-05-26 | Worked on minor refinements suggestions for introduction chapter.
2026-05-28 | Meeting with supervisor, revised cleaner objectives, discussed literature review outline, updated supervisor on changes in choice of data sources and potential approaches in methodology.
2026-06-03 | First section of literature review complete, start second section of literature review and continue exploring on methodologies.
2026-06-09 | Meeting with supervisor, discussed some minor methodology uncertainties and finer details of methodology approach with supervisor.
2026-06-09 | Continue working on literature review, started retrieving data on Google Earth Engine
2026-06-12 | Revised early sections of literature review and continue other sections of literature review.
2026-06-19 | Review methodological approaches in existing literature for informing methodology for this study
2026-06-28 | Completed first full draft for literature review, proceeded on to methodology.
2026-06-30 | Setup a GitHub repository and R project for analysis and submission.
2026-07-02 | Completed remote sensing analysis (Stage 1), updated Google Earth Engine scripts to GitHub repository.
2026-07-07 | Encountered data ambiguities in running r5r travel time matrices, where origin (from_id) and destination values (to_id) reversed (for Walking and Cycling modes) under the whole Greater London computation using package version 2.3.0. Identified problem to be raised from versions issues, updated and re-computed travel time matrices.
2026-07-18 | Completed analysis (Stage 2 and 3) and edited initial figures and outputs.
2026-07-23 | Meeting with supervisor, discussed some uncertainties in the final step of methodology and shared initial results and figure outputs.
2026-07-27 | Wrapped up methodology section and proceed to writing results and discussion.
2026-08-03 | Edited format as required according to the dissertation handbook, draft sent to supervisor.
2026-08-12 | Final sections and figures completed.
2026-08-13 | Revise draft.
2026-08-18 | Meeting with supervisor, clarification of any final questions on final draft.
2026-08-29 | Tidy GitHub repository for submission.
2026-08-31 | Final edits.